## 7-Day Build Plan
Cueword - 7-Day Production Build Plan
Engineering-hours. The 7 'days' are workstream phases compressed into wall-clock by running independent tasks as parallel agents. Scope: limited pilot + admin panel + tutor-stats dashboard - Zoom link kept - real Claude AI. Defers legal/COPPA, pen-test, UAT to fast-follow.
Day | Phase / Workstream | Task | Est. Hrs | Status | Needs
Day 1 | Foundations (Phase 0 + 1.0) | Schema: 14 new tables + extend profiles/sessions/stories | 6 | Done
|  | Row types wired into @cueword/core (no any) | 2 | Done
|  | Auth core: @supabase/ssr + server client + DAL | 3 | Done
|  | proxy.ts + Supabase login/logout (Next 16) | 6 | To do
|  | Retire localStorage auth + provision auth users | 5 | To do
|  | Migration 0003: auth-scoped RLS + tests | 7 | To do
|  | Staging env + CI gate | 5 | To do
Day 1 subtotal
Day 2 | Student app on real data (Phase 1) | Student query layer + pilot seed | 8 | To do
|  | Home dashboard | 4 | To do
|  | My Stories (curriculum + assignments) | 4 | To do
|  | My Workouts (drills + auto-flagging) | 5 | To do
|  | Schedule (2/wk cap, cancel rule, timezone) | 4 | To do
|  | My Progress (belts, KPIs, milestones) | 4 | To do
|  | My Portfolio | 3 | To do
Day 2 subtotal
Day 3 | Coach app on real data (Phase 1) | Coach query layer + KPI views + seed | 10 | To do
|  | Dashboard (live hero, KPIs, tasks inbox) | 5 | To do
|  | Roster + student detail | 5 | To do
|  | Schedule + Attendance | 8 | To do
|  | Curriculum browser | 4 | To do
|  | Marking + per-item | 6 | To do
|  | Comms + Profile | 6 | To do
Day 3 subtotal
Day 4 | Live class hardened (Phase 2) | Multi-session (off the single fixed row) | 8 | To do
|  | Join-the-right-session routing | 3 | To do
|  | Realtime resilience (reconnect / late-join) | 8 | To do
|  | Driver / take-over edge cases | 4 | To do
|  | Zoom auto-link per session | 6 | To do | Zoom creds
|  | Perf + multi-session E2E | 6 | To do
Day 4 subtotal
Day 5 | Real AI - Claude (Phase 3) | AI service (SDK + structured rubric output) | 4 | To do | Anthropic key
|  | Writing feedback | 6 | To do | Anthropic key
|  | Speaking (audio -> transcribe -> score) | 10 | To do | Anthropic key
|  | Audio storage + signed URLs | 4 | To do
|  | Coach marking-assist (AI draft) | 4 | To do | Anthropic key
|  | Eval harness + kid-safety guardrails | 8 | To do
|  | Cost controls + PostHog usage logging | 5 | To do
Day 5 subtotal
Day 6 | Admin panel + tutor-stats (Phases 4+5) | Scaffold admin app + admin-role auth | 6 | To do
|  | People CRUD + invite (auth user + profile) | 8 | To do
|  | Enrollments + scheduling + Zoom assign | 10 | To do
|  | Assign stories / sequence curriculum | 5 | To do
|  | Content pipeline (migrate 9 stories + editor) | 10 | To do
|  | Provisioning audit log | 3 | To do
|  | Tutor-stats: metrics SQL views | 6 | To do
|  | Tutor-stats: dashboard UI (charts / filters) | 8 | To do
|  | Tutor-stats: 3rd-party access + CSV/PDF export | 10 | To do
Day 6 subtotal
Day 7 | Polish, tests, deploy (Phases 6-7) | Error / empty / loading states | 8 | To do
|  | Timezone correctness end-to-end | 5 | To do
|  | Accessibility pass | 6 | To do
|  | Notifications + email reminders | 6 | To do
|  | Test expansion (unit / integration / E2E) | 12 | To do
|  | Observability (PostHog funnels + alerts) | 5 | To do
|  | Deploy to staging + smoke test | 8 | To do | Vercel access
|  | Runbook + pilot reset/seed script | 4 | To do
Day 7 subtotal
CORE BUILD TOTAL
TOTAL WITH +20% BUFFER
| Status: | Done = shipped in the Day-1 build session (schema + types + auth core, verified green).
| Queue now: | Anthropic key -> Day 5 (AI) ¦ Vercel access -> Day 7 (deploy) ¦ Zoom creds + DNS -> Day 4/7.